## Sheet1
No. | Item | Details | Recorded date | Plan | Status
1 | Control to be changed | The vehicle selection autocomplete to be changed with searchable dropdown same as Employee master | 2020-04-04 |  | Completed
2 | Check SAVE condition | If OWN VEHICLE selected, then system should not SAVE if we enter OTHER VEHICLE number | 2020-04-04 |  | Completed
3 | Service Entry photo save path | Photos to be saved in folder and URL to be kept in DB | 2020-04-04 |  | Completed
4 | Camera not displaying | Camera not showing after hosting to server and opening in client laptop | 2020-07-04 |  | Pending
5 | On page refresh error | Not found error showing if we refresh the page | 2020-07-04 |  | Pending
6 | Slow page | View Service entry page is very slow | 2020-07-04 |  | Pending
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
85
86
87
88
89
90
91
92
93
94

## Sheet2
Pending
In progress
Completed