## General
No. | Item | Details | Recorded By | Recorded date | Plan | Status | Comments | Changed By
1 | Authentication | DB & Active Directory Authentication | Renju | 2020-03-04 |  | Pending |  | Renju
2 | Maintain a table To describe system features | Bilingual,Authentication Mode,Multycompany ? | Renju |  |  | Completed |  | Lijina
3 | Organization Structure | Company,LocationGroup,Location,Division | Renju | 2020-03-04 |  | Pending |  | Renju
4 | Have to discuss more on "DEPARTMENTS" |  | Renju |  |  | Pending |  | Renju
5 | FileAttach Option To be included in all pages |  | Renju |  | This is to be done immediately. Otherwise later we have to go back and change everywhere | Pending |  | Renju
6 | Dynamic workflow |  | Renju |  |  | Pending |  | Renju
7 | The jQury added by Arun to fix GRID LINE EXPANSION in Workshop module to be replaced with AngularJS |  | Renju | 2020-04-04 |  | Pending |  | Renju
8 | Grid sorting | Sorting ASC/DESC to be implemeneted in grid | Renju | 2020-04-04 | This is to be done immediately. Otherwise later we have to go back and change everywhere | Completed |  | Lijina
9 | Grid searching | filtered search to be implemented in grid | Renju | 2020-04-04 | This is to be done immediately. Otherwise later we have to go back and change everywhere | In progress |  | Lijina
10 | User & Role management | To be implemented - dynamic | Renju | 2020-04-04 |  | In progress |  | Lijina
11 | Paging | Grid paging with: Page No., FIRST,LAST,PREVIOUS,NEXT,No. of rows selection etc | Renju |  |  | Pending |  | Renju
12 | Logged in user detailss display | Along with the logged in username display on top, show USER ROLE also | Renju |  |  | Completed |  | Lijina
13 | Menu scroll | Separate scroll bar for menu to be added so that when menu scrolls, the other part should not scroll | Renju |  |  | Pending |  | Renju
14 | Top header freeze | TOP HEADER to be frozen so that when page scrolls, header should not move | Renju |  |  | Pending |  | Renju
15 | Search above Menu | Make the SEARCH BOX above functional, else hide it | Renju |  |  | Pending |  | Renju
16 | Remember password | Login page remember password should be functional | Renju |  |  | Pending |  | Renju
17 | Loginname autocomplete remove | Remove autocomplete in loginname field | Renju |  |  | Pending |  | Renju
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
85
86
87
88
89
90
91
92
93
94

## Service Module
No. | Item | Details | Recorded By | Recorded date | Plan | Status | Comments | Changed By
1 | Control to be changed | The vehicle selection autocomplete to be changed with searchable dropdown same as Employee master | Renju | 2020-04-04 |  | Pending |  | Renju
2 | Check SAVE condition | If OWN VEHICLE selected, then system should not SAVE if we enter OTHER VEHICLE number | Renju | 2020-04-04 |  | Pending |  | Renju
3 | Service Entry photo save path | Photos to be saved in folder and URL to be kept in DB | Renju | 2020-04-04 |  | Pending |  | Renju
4 | Camera not displaying | Camera not showing after hosting to server and opening in client laptop | Renju | 2020-07-04 |  | Pending |  | Renju
5 | On page refresh error | Not found error showing if we refresh the page | Renju | 2020-07-04 |  | Pending |  | Renju
6 | Slow page | View Service entry page is very slow | Renju | 2020-07-04 |  | Pending |  | Renju
7 | Arabic entry in Service type |  | Renju | 15/03/2020 |  | Completed
8 | In bill, show both English & Arabic |  | Renju | 15/03/2020 |  | Completed
9 | Own/TP in Pricing to be changed to Manual/Auto |  | Renju | 15/03/2020 |  | Completed
10 | Opening count entry - There should be a provision to enter the starting count of Automatic service machine. Service entry for the day should be allowed only after this. Next day, the new entry to be matched with our system count and if there is mismatch, it should be highlited in dashboard |  | Renju | 15/03/2020 |  | In progress
11 | Bill - For own vehicle, show full discount and total to be 0. |  | Renju | 15/03/2020 |  | Completed
12 | Report - Own vehicle to be shown as 0. Actuals also to be shown in another column |  | Renju | 15/03/2020 |  | Pending
13 | Thermal printer check |  | Renju | 15/03/2020 |  | Pending
14 | Check TAB with blutooth or wireless camera |  | Renju | 15/03/2020 |  | Pending
15 | Service entry layout - Servive types as TABS/BOXES to select |  | Renju | 15/03/2020 |  | Completed
16 | Fleet selection in Service entry - To be filtered list |  | Renju | 15/03/2020 |  | Completed
17 | Service entry - Fleet/Type selection change and controls reset |  | Renju | 15/03/2020 |  | Completed
18 | Fleet types - Page to be completed |  | Renju | 15/03/2020 |  | Completed
19 | Dashboard: Today's service - Manual - Own Today's service - Manual - TP Today's service - Auto - Own Today's service - Auto - TP ------------------------------------------ Service type wise count of Manual/Auto/Own/TP ------------------------------------------ Graph: Last 7 days |  | Renju | 15/03/2020 |  | In progress
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
85
86
87
88
89
90
91
92
93

## HR Payroll
No. | Item | Details | Recorded By | Recorded date | Plan | Status | Comments | Changed By
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
85
86
87
88
89
90
91
92
93
94

## Workshop
No. | Item | Details | Recorded By | Recorded date | Plan | Status | Comments | Changed By
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
85
86
87
88
89
90
91
92
93
94

## Fleet
No. | Item | Details | Recorded By | Recorded date | Plan | Status | Comments | Changed By
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
85
86
87
88
89
90
91
92
93
94

## list (hidden)
Pending | Renju
In progress | Lijina
Completed | Arun