## Sheet1
Page Name | Start Date | Days Required | Actual Completion date | Status | Comments
Salary Setup | 2020-04-11 | 1 |  | Pending
Salary Increment | 2020-04-12 | 2 |  | Pending
Shift Configuration | 2020-04-14 | 2 |  | Pending
Leave Slab (To be added in Emp Master) | 2020-04-16 | 1 |  | Pending
Leave Configurations | 2020-04-17 | 1 |  | Pending
Attendance Entry | 2020-04-18 | 3 |  | Pending
View/Edit/Approve Attendance | 2020-04-21 | 1 |  | Pending
Leave Application | 2020-04-22 | 1 |  | Pending
Leave Approval | 2020-04-23 | 1 |  | Pending
Leave Settlement | 2020-04-24 | 1 |  | Pending
EOS | 2020-04-25 | 1 |  | Pending
Salary Process | 2020-04-26 | 2 |  | Pending
Rollback Payroll | 2020-04-27 | 1 |  | Pending
Other Payments | 2020-04-28 | 1 |  | Pending

## Sheet2
Pending
In progress
Completed